## Sheet1
Requirement ID | Description of requirement | Story Points | Priority | Sprint No.
1 | Research how modern password managers work. How do they store passwords on the computer, in an extension and within an application? Are they always accesible to the user or is there some authentication required? | 1 | 1 | 1
2 | Research chrome extensions. When creating one, does a developer have to use some sort of chrome proprietary language? Or can we write our own then export it? What security access do extensions have towards the built-in password manager in Chrome, and how can we improve on it? | 3 | 1 | 1
3 | Research GUI options in CPP / C / other. Once we pick our language, research how GUIs are created within that language. Is it hard to create GUIs in that language, or are there frameworks we can use to help with design? | 2 | 1 | 1
4 | Pick Language: Discuss as a team in what language we want to implement our project. This needs to be chosen first so then the GUI options can be chosen and how this language may interact with extensions, as well as cut down on learning time within the team. | 1 | 1 | 1
5 | Research how steganography can be used to better secure our password manager, if at all. How does steganography compare to modern password managers and what extra use for the user are we adding? | 2 | 2 | 1
6 | Do we need to use a third party for authenticating users within the password manager? Such as a certificate, biometric data, 2 factor, etc. Or are we going to assume the user is the owner of the computer and do not need to authenticate | 2 | 2 | 2
7 | Initial GUI design: Decide what the user interface should look like. What buttons do we need? Where will the search bar be located, should there be a logo on it? Decide so the implementation can build from this. | 8 | 1 | 1
8 | GUI implementation: Create the GUI using whatever GUI builder we found for our language. This should call functions from the backend on user interaction, and minimize CPU load with graphics | 13 | 2 | 2
9 | Research securely storing passwords: Research needs to be done on how passwords can be stored on a user's computer securely. Whichever way we store them, the passwords should only be accessible if the user can log into the password manager. | 2 | 2 | 2
10 | Search bar: Implement the functionality to search through your current passwords by substring | 3 | 3 | 3
11 | Sorting function: The passwords should be displayed to the user in alphabetical order by website name. There should be a sorting function to display it in this manner. | 3 | 4 | 3
12 | Filter function: Along with a search bar, the user should have a way to filter through their passwords. For example, searching for website that have auto-generated passwords. | 3 | 4 | 3
13 | Lock password storage:Since we are storing the passwords from the user on their local computer, we need to keep them secure from access outside of our application. When our application is closed, lock and encrypt the password file so no user can access it unless our program is running. | 5 | 3 | 3
14 | Unlocking password storage: Storing encryption key for locked password file on program exit and using this encryption key to unlock password file on program startup. | 3 | 3 | 3
15 | Auto-fill: Getting passwords from PWM to Password needer | 13 | 5 | 4
16 | The ability to add a password to the manager: the user tells password manager what website this password is for, and it saves it | 3 | 1 | 2
17 | Authentication for User. On application run, the user needs to log in. They can choose what credentials they use to log in but should be multiple options, and a none option if a user desires. | 3 | 2 | 2
18 | Edit passwords: Current passwords must be able to be updated if the user is logged in. | 2 | 2 | 2
19 | Lookup to see if passwords have been compromised: Use breach databases (like for example, Have I Been Pwned) then warn users if their password has been/potentially has been leaked | 8 | 5 | 4
20 | Show security of password: When a user enters their own password, show how secure it is (What makes a password secure?) | 2 | 3 | 3
21 | Generate password: Implement the functionality to generate a password for a website. This could be through random generation with the user providing parameters like length, or generating passwords from user-related word lists. | 5 | 1 | 1